## Lab 1
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Anandarajan Sindini | Kolady Anamika Martin | Verma Nandini | Duong Ngoc Yen | Chua Jim Sean
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Happy
1 | Updating Use Case Description | Task Quality Evaluation (After Task Completed) | 9 |  |  |  |  | 7.3333 | 6.5 | 2 | Duong Ngoc Yen | Kolady Anamika Martin | Through Discussion
| Estimated Task Priority（0-10） |  | 8 | 7 |  |  | 7
| Estimated Task Difficulty（0-10） |  |  | 5 |  |  | 8
| Estimated Time Required for the Task（1-14 Days） |  |  | 2 |  |  | 2
| Team Member's Confidence about the Task (0-10) |  |  | 9 |  |  | 8
2 | Creating Use Case Diagram | Task Quality Evaluation (After Task Completed) | [5 empty] | 8 | 5.5 | 1.5 | Anandarajan Sindini | Verma Nandini | Through Discussion
| Estimated Task Priority（0-10） |  |  | 8 |  |  | 8
| Estimated Task Difficulty（0-10） |  |  | 6 |  |  | 5
| Estimated Time Required for the Task（1-14 Days） |  |  | 1 |  |  | 2
| Team Member's Confidence about the Task (0-10) |  |  | 6 |  |  | 7
3 | Back-end for Web Application | Task Quality Evaluation (After Task Completed) | [5 empty] | 9.5 | 7.5 | 8.5 | Chua Jim Sean | Anandarajan Sindini | Through Discussion
| Estimated Task Priority（0-10） |  |  | 10 |  |  | 9
| Estimated Task Difficulty（0-10） |  |  | 8 |  |  | 7
| Estimated Time Required for the Task（1-14 Days） |  |  | 9 |  |  | 8
| Team Member's Confidence about the Task (0-10) |  |  | 7 |  |  | 7
4 | Front-end for Web Application | Task Quality Evaluation (After Task Completed) | [5 empty] | 9 | 8.5 | 9 | Kolady Anamika Martin | Verma Nandini | Through Discussion
| Estimated Task Priority（0-10） |  |  | 9 |  |  | 9
| Estimated Task Difficulty（0-10） |  |  | 8 |  |  | 9
| Estimated Time Required for the Task（1-14 Days） |  |  | 9 |  |  | 9
| Team Member's Confidence about the Task (0-10) |  |  | 10 |  |  | 7

## Lab 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Anandarajan Sindini | Kolady Anamika Martin | Verma Nandini | Duong Ngoc Yen | Chua Jim Sean
Team member's mood during the this week's meeting: |  |  | Happy | Excited | Excited | Excited | Neutral
1 | Update Lab 1 Deliverable: Use Case Model and Project Proposal | Task Quality Evaluation (After Task Completed) | 7 | 6 | 6 | 9 | 8 | 5.2 | 4 | 2.4 | Verma Nandini | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 6.8667
| Estimated Task Priority（0-10） |  | 5 | 6 | 5 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 3 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10
2 | Complete System Requirements Specification | Task Quality Evaluation (After Task Completed) | 8 | 9 | 9 | 9 | 8 | 9.2 | 8.6 | 4.75 | Chua Jim Sean | Duong Ngoc Yen | Through Discussion | Yes | 1 | Excited | 8.7
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 9 | 7 | 8 | 9 | 10
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 |  | 5 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 |  | 8 | 7
3 | Complete Quality Plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 9 | 9 | 8 | 9 | 8.6 | 5.6 | Kolady Anamika Martin | Verma Nandini | Through Discussion | Yes | 5 | Excited | 8.6667
| Estimated Task Priority（0-10） |  | 9 | 10 | 10 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 10 | 9 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 8 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 8 | 7 | 7
4 | Complete Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 5.2 | 3.2 | 1.2 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 9.2
| Estimated Task Priority（0-10） |  | 6 | 7 | 7 | 3 | 3
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 2 | 1 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 10 | 10

## Lab 3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Anandarajan Sindini | Kolady Anamika Martin | Verma Nandini | Duong Ngoc Yen | Chua Jim Sean
Team member's mood during the this week's meeting: |  |  | Happy | Happy | Happy | Happy | Happy
1 | Update previous Deliverables | Task Quality Evaluation (After Task Completed) | 7 | 8 | 8 |  | 9 | 4.5 | 5.5 | 2.25 | Verma Nandini | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 7.3
| Estimated Task Priority（0-10） |  | 6 | 4 | 4 |  | 4
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 |  | 5
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 2 |  | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 |  | 8
2 | Risk Management Plan | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 |  | 8 | 8.25 | 5 | 3 | Chua Jim Sean | Duong Ngoc Yen | Through Discussion | Yes | 1 | Excited | 8.05
| Estimated Task Priority（0-10） |  | 9 | 8 | 7 |  | 9
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 5 |  | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 1 | 2 |  | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 |  | 7
3 | Project Plan | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 |  | 9 | 7.5 | 6 | 2.5 | Kolady Anamika Martin | Verma Nandini | Through Discussion | Yes | 5 | Excited | 8.3
| Estimated Task Priority（0-10） |  | 8 | 7 | 8 |  | 7
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 7 |  | 4
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 1 | 2 |  | 5
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 8 |  | 4
4 | Complete Meeting Minutes | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 |  | 7 | 1.75 | 1.5 | 1.5 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 6.75
| Estimated Task Priority（0-10） |  | 2 | 1 | 1 |  | 3
| Estimated Task Difficulty（0-10） |  | 2 | 0 | 1 |  | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 |  | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 |  | 10
5 | Prototype for Demonstration | Task Quality Evaluation (After Task Completed) | 6 | 6 | 6 |  | 6 | 9.5 | 9.75 | 7.5 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 6.7
| Estimated Task Priority（0-10） |  | 9 | 10 | 10 |  | 9
| Estimated Task Difficulty（0-10） |  | 10 | 9 | 10 |  | 10
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 6 | 6 |  | 10
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 |  | 7
6 | SVN: Code, Documents, Slides, Video Clips, etc. | Task Quality Evaluation (After Task Completed) | 8 | 6 | 8 |  | 6 | 9.25 | 7.75 | 5.5 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 7.45
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 |  | 10
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 8 |  | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 7 | 5 |  | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 |  | 7

## Lab 4
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Anandarajan Sindini | Kolady Anamika Martin | Verma Nandini | Duong Ngoc Yen | Chua Jim Sean
Team member's mood during the this week's meeting: |  |  | Happy | Happy | Happy | Happy | Happy
1 | Update previous Deliverables | Task Quality Evaluation (After Task Completed) | 8 | 10 | 8 | 9 | 9 | 5 | 5.6 | 3.2 | Verma Nandini | Anandarajan Sindini | Through Discussion | Yes | 1 | Excited | 8.1667
| Estimated Task Priority（0-10） |  | 6 | 6 | 4 | 5 | 4
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 2 | 7 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 | 8 | 8
2 | Update Use case Diagram | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 9 | 8 | 7.5 | 4.5 | 2.75 | Chua Jim Sean | Duong Ngoc Yen | Through Discussion | Yes | 1 | Excited | 8.0833
| Estimated Task Priority（0-10） |  | 7 | 7 | 7 |  | 9
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 5 |  | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 2 |  | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 |  | 7
3 | Back-end development | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 7 | 9 | 8.2 | 6.6 | 3.8 | Kolady Anamika Martin | Verma Nandini | Through Discussion | Yes | 7 | Excited | 8.2
| Estimated Task Priority（0-10） |  | 10 | 9 | 8 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 10 | 6 | 7 | 6 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 1 | 2 | 4 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 7 | 8 | 9 | 4
4 | Front-end development | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 8 | 7 | 5 | 2.8 | 3.8 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 7 | Excited | 7.6667
| Estimated Task Priority（0-10） |  | 10 | 10 | 1 | 1 | 3
| Estimated Task Difficulty（0-10） |  | 9 | 0 | 1 | 1 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 1 | 1 | 7 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 10 | 8 | 10
5 | Design Report on Software Maintainability | Task Quality Evaluation (After Task Completed) | 8 | 9 | 6 | 6 | 6 | 8.6 | 8.8 | 5.8 | Kolady Anamika Martin | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 7.2667
| Estimated Task Priority（0-10） |  | 7 | 8 | 10 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 10 | 8 | 10
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 6 | 6 | 5 | 10
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 | 6 | 7
6 | Configuration Management Plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 7 | 6 | 7.2 | 7.4 | 5 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 2 | Excited | 7.5333
| Estimated Task Priority（0-10） |  | 7 | 5 | 9 | 5 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 8 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 7 | 5 | 6 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 | 7 | 7
7 | Release Plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 8 | 6 | 8 | 7.2 | 4.8 | Kolady Anamika Martin | Verma Nandini | Through Discussion | Yes | 2 | Excited | 7.8333
| Estimated Task Priority（0-10） |  | 8 | 5 | 9 | 8 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 8 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 7 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 8 | 6 | 7 | 4 | 7
8 | Change Management Plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 7 | 6 | 7.4 | 7.6 | 5 | Jim Sean | Anandarajan Sindini | Through Discussion | Yes | 2 | Excited | 7.5667
| Estimated Task Priority（0-10） |  | 8 | 5 | 9 | 5 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 8 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 7 | 5 | 7 | 5
| Team Member's Confidence about the Task (0-10) |  | 8 | 6 | 7 | 7 | 7
9 | Slides For Presentation | Task Quality Evaluation (After Task Completed) | 9 | 10 | 8 | 8 | 6 | 9.2 | 7.6 | 5 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 2 | Excited | 8.3667
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 8 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 8 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 7 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 8 | 6 | 7 | 6 | 7

## Lab 5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Anandarajan Sindini | Kolady Anamika Martin | Verma Nandini | Duong Ngoc Yen | Chua Jim Sean
Team member's mood during the this week's meeting: |  |  | Happy | Happy | Happy | Happy | Happy
1 | Update previous Deliverables | Task Quality Evaluation (After Task Completed) | 8 | 10 | 8 | 9 | 9 | 5 | 5.6 | 3.2 | Anandarajan Sindini | Chua Jim Sean | Through Discussion | Yes | 1 | Excited | 8.1667
| Estimated Task Priority（0-10） |  | 6 | 6 | 4 | 5 | 4
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 2 | 7 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 | 8 | 8
2 | Update Use case Diagram | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 9 | 8 | 7.5 | 4.5 | 2.75 | Chua Jim Sean | Duong Ngoc Yen | Through Discussion | Yes | 1 | Excited | 8.0833
| Estimated Task Priority（0-10） |  | 7 | 7 | 7 |  | 9
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 5 |  | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 2 |  | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 |  | 7
3 | Complete Test Plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 7 | 9 | 8.2 | 6.6 | 3.8 | Kolady Anamika Martin | Verma Nandini | Through Discussion | Yes | 7 | Excited | 8.2
| Estimated Task Priority（0-10） |  | 10 | 9 | 8 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 10 | 6 | 7 | 6 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 1 | 2 | 4 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 7 | 8 | 9 | 4
4 | Complete Test Coverage Report | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 8 | 7 | 5 | 2.8 | 3.8 | Duong Ngoc Yen | Anandarajan Sindini | Through Discussion | Yes | 7 | Excited | 7.6667
| Estimated Task Priority（0-10） |  | 10 | 10 | 1 | 1 | 3
| Estimated Task Difficulty（0-10） |  | 9 | 0 | 1 | 1 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 1 | 1 | 7 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 10 | 8 | 10
5 | Complete Test Cases and Requirements | Task Quality Evaluation (After Task Completed) | 8 | 9 | 6 | 6 | 6 | 8.6 | 8.8 | 5.8 | Kolady Anamika Martin | Anandarajan Sindini | Through Discussion | Yes | 4 | Excited | 7.2667
| Estimated Task Priority（0-10） |  | 7 | 8 | 10 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 10 | 8 | 10
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 6 | 6 | 5 | 10
| Team Member's Confidence about the Task (0-10) |  | 7 | 6 | 7 | 6 | 7